## Risk Register
RISK REGISTER | [7 empty] | Risk Evaluation |  |  |  | Risk Treatment |  |  |  | Others
Risk ID | Asset ID | Asset Name | Risk Description | Risk Category | Threat | Vulnerability | Risk Level | Impact (I) | Likelihood (L) | Asset Risk Value (A) | Risk Rating = I*L*A | Risk Treatment | Remediation Actions | Target Date | Justification if Risk Accepted | Risk Owner | Observations | Control
R001 | A001 | CEO Laptop | Risk of data theft due to weak password | Digital | Data Theft | Weak password | High | 5 | 4 | 3 | 60 | Mitigate | Enforce MFA, reset all weak passwords, implement password complexity rules, and conduct immediate password audit | 2027-10-05 | N/A | IT Support Engineer | Critical executive asset; high exposure due to privileged access | Strong password policy with MFA enforcement
R002 | A002 | CTO Laptop | Risk of malware attack due to unpatched system | Digital | Malware Attack | Unpatched system | Medium | 5 | 3 | 3 | 45 | Mitigate | Apply latest OS and software patches, enable automatic updates, and run full system vulnerability scan | 2027-12-05 | N/A | IT Support Engineer | System security dependent on timely patching; currently vulnerable | Antivirus protection and regular patch updates
R003 | A003 | HR System | Risk of data leakage due to improper access control | Digital | Data Leakage | Improper access control | Medium | 4 | 3 | 3 | 36 | Mitigate | Review all user roles, remove excessive permissions, implement RBAC, and audit access logs | 14/05/2027 | N/A | HR & Finance Specialist | Sensitive HR data; access control weaknesses increase privacy risk | Role-based access control implementation
R004 | A004 | Finance Database | Risk of unauthorized access due to weak authentication | Digital | Unauthorized Access | Weak authentication | High | 5 | 4 | 3 | 60 | Mitigate | Enable MFA for all users, enforce strong authentication policies, and encrypt sensitive financial data | 16/05/2027 | N/A | HR & Finance Specialist | Highly critical financial data; strong protection required | Encryption and multi-factor authentication
R005 | A005 | Security Monitoring Tool | Risk of failure due to misconfiguration | Technical | Tool Failure | Misconfiguration | Medium | 4 | 3 | 3 | 36 | Mitigate | Review current configurations, correct misconfigurations, and validate tool functionality through testing | 18/05/2027 | N/A | Security Engineer | Tool reliability depends on correct configuration; needs regular validation | Regular configuration review and validation
R006 | A006 | IT Support Laptop | Risk of device theft due to lack of physical security | Physical | Device Theft | No physical security | Low | 3 | 3 | 2 | 18 | Mitigate | Implement device locking, enable tracking software, and assign asset tags for identification | 20/05/2027 | N/A | IT Support Engineer | Portable device with higher theft risk; physical controls required | Device lock, asset tagging, and tracking
R007 | A007 | Cloud Infrastructure | Risk of downtime due to dependency on provider | Technical | Service Downtime | Dependency on provider | Medium | 5 | 3 | 3 | 45 | Transfer | Establish backup environment, configure failover mechanisms, and review SLA with provider | 22/05/2027 | N/A | Cloud Security Engineer | External dependency introduces availability and vendor risk | Backup systems and SLA agreements
R008 | A008 | Pen Testing Toolkit | Risk of unauthorized use due to lack of access control | Digital | Unauthorized Use | Lack of access control | Low | 4 | 2 | 3 | 24 | Mitigate | Restrict access to authorized users, implement authentication controls, and maintain usage logs | 24/05/2027 | N/A | Penetration Testing Specialist | High-risk tool; misuse can cause serious security impact | Restricted access with role-based permissions
R009 | A009 | Security Logs | Risk of log tampering due to lack of integrity checks | Digital | Log Tampering | No integrity checks | Medium | 4 | 3 | 3 | 36 | Mitigate | Enable log integrity checks (hashing), restrict access, and implement centralized log monitoring | 26/05/2027 | N/A | Security Analyst | Integrity of logs is essential for incident detection and audits | Log monitoring with hashing and integrity validation
R010 | A010 | Project Mgmt Tool | Risk of data loss due to lack of backup | Digital | Data Loss | No backup | Medium | 3 | 3 | 3 | 27 | Mitigate | Configure automated backups, test data recovery process, and ensure backup retention policy | 28/05/2027 | N/A | Project Manager | Lack of backup impacts project continuity and recovery capability | Regular automated backups with recovery testing
R011 | A011 | Client Database | Risk of data breach due to weak access control | Digital | Data Breach | Weak access control | High | 5 | 4 | 3 | 60 | Mitigate | Encrypt sensitive data, enforce strict access controls, and conduct periodic access reviews | 30/05/2027 | N/A | Service Delivery Manager | Contains highly sensitive client data; breach impact is severe | Encryption and strict access control policies
R012 | A012 | Implementation Server | Risk of system failure due to lack of redundancy | Technical | System Failure | No redundancy | Medium | 5 | 3 | 3 | 45 | Mitigate | Implement redundancy and failover systems, and test system recovery mechanisms | 2027-01-06 | N/A | Cloud Implementation Engineer | System availability risk due to lack of redundancy | Failover systems and redundancy implementation
R013 | A013 | CRM System | Risk of data leakage due to misconfigured permissions | Digital | Data Leakage | Misconfigured permissions | Medium | 4 | 3 | 3 | 36 | Mitigate | Review permission settings, correct misconfigurations, and enforce least privilege access | 2027-03-06 | N/A | Business Operations Manager | Misconfigured permissions can lead to unintended data exposure | Access control review and permission management
R014 | A014 | Support System | Risk of unauthorized access due to weak credentials | Digital | Unauthorized Access | Weak credentials | Medium | 3 | 3 | 3 | 27 | Mitigate | Enforce strong password policy, enable MFA, and remove inactive or weak accounts | 2027-05-06 | N/A | Customer Support Executive | Weak credentials increase risk of unauthorized access | Strong password enforcement and access control
R015 | A015 | Risk Register | Risk of data manipulation due to lack of access restriction | Governance | Data Manipulation | No access restriction | Low | 4 | 2 | 3 | 24 | Mitigate | Restrict editing access, enable version control, and maintain audit logs of changes | 2027-07-06 | N/A | ISMS Lead | Integrity of risk records is critical for compliance and audits | Restricted access and audit logging
R016 | A016 | Compliance Docs | Risk of data loss due to lack of backup | Digital | Data Loss | No backup | Medium | 4 | 3 | 3 | 36 | Mitigate | Implement secure backup solution, ensure document encryption, and restrict unauthorized access | 2027-09-06 | N/A | Compliance Specialist | Compliance data loss can lead to regulatory issues | Regular automated backup and secure storage
R017 | A017 | Audit Reports | Risk of data exposure due to improper storage | Digital | Data Exposure | Improper storage | Medium | 5 | 2 | 3 | 30 | Mitigate | Store reports in secure location, restrict access, and apply encryption where required | 2027-11-06 | N/A | Security Auditor | Improper storage may expose confidential audit findings | Secure storage with restricted access controls
R018 | A018 | Operations Dashboard | Risk of downtime due to server issues | Technical | System Downtime | Server issues | Medium | 3 | 3 | 3 | 27 | Mitigate | Set up real-time monitoring, configure alerts, and ensure server health checks | 13/06/2027 | N/A | Operations Coordinator | System downtime affects operational visibility and decision-making | Real-time monitoring and alerting system
R019 | A019 | Business Reports | Risk of data errors due to manual handling | Operational | Data Error | Manual handling | Low | 3 | 2 | 2 | 12 | Accept | Implement data validation rules, reduce manual intervention, and introduce review workflow | 15/06/2027 | Impact minimal; controls in place are adequate | Business Analyst | Manual process increases chances of human error | Data validation and review checks
R020 | A020 | Tracking Sheet | Risk of data loss due to lack of version control | Digital | Data Loss | No version control | Low | 3 | 2 | 2 | 12 | Accept | Enable version control system, maintain backup copies, and restrict editing permissions | 17/06/2027 | Minimal risk; improvements planned; existing controls adequate | Finance & Admin Executive | Lack of version control may lead to data inconsistency | Version control system and backups
Risk Owner Reference Table
|  | Role | Risk Owner
|  | IT Support Engineer | Teddy Yu
|  | HR & Finance Specialist | Reese Miller
|  | Security Engineer | Rohith Varma
|  | Cloud Security Engineer | Karthick
|  | Penetration Testing & Incident Response Specialist | Ananya
|  | Security Analyst | Vidhya
|  | Project Manager | Connor Hamilton
|  | Service Delivery Manager | Mahendran
|  | Cloud Implementation Engineer | Nick Sharma
|  | Business Operations Manager | Amith
|  | Customer Support Executive | Reena
ISMS Lead
|  | Compliance Specialist | Sanjay Patel
|  | Security Auditor | Rufus Stewart
|  | Operations Coordinator / Finance & Admin Executive | Sunil
|  | Business Analyst | Ajmal

## Guidelines
1. Risk Rating Methodology |  |  |  |  | 2. Risk Level- Inherent Risk and Residual Risk
High impact. Risk needs to be treated/ transferred
Risk is calculated using the following formula: | [5 empty] | Medium impact. Risk needs to be treated/ transferred. Justification required for Risk acceptance
Risk Rating = Impact (I) × Likelihood (L) × Asset Value (A) | [5 empty] | Low impact. Risk can be accepted.
Where:
Impact (I): Severity of consequence if the risk occurs
Likelihood (L): Probability of occurrence
Asset Value (A): Criticality of the asset
3. Risk Rating Scale and Classification
Risk Rating Range | Qualitative Level | Risk Value | Definition |  |  | 4. Risk Level Guidance
51 – 75 | High |  | Controls are partially effective; risk is significant and requires immediate treatment or transfer |  |  | Risk Level | Description
26 – 50 | Medium |  | Controls are insufficient; improvement or additional controls are required |  |  | High | High impact risk; must be treated or transferred immediately
0 – 25 | Low |  | Risk is low; existing controls are adequate or risk can be accepted |  |  | Medium | Moderate risk; should be treated or transferred; justification required if accepted
[6 empty] | Low | Low risk; can be accepted with monitoring
4. Risk Impact Scale |  |  |  | 5. Risk Likelihood Table
Value | Impact Level | Description |  | Value | Likelihood | Description
5 | Catastrophic | Severe business impact |  | 5 | Almost Certain | Very frequent
4 | Major | High impact |  | 4 | Probable | Likely
3 | Moderate | Noticeable impact |  | 3 | Possible | Occasional
2 | Minor | Low impact |  | 2 | Unlikely | Rare
1 | Negligible | Minimal Impact |  | 1 | Rare | Very rare

## List of Threat & Vulnerability
Category | Threat | Vulnerability | Category | Threat | Vulnerability | Category | Threat | Vulnerability
Hardware | Equipment Failure | Inadequate maintenance | Network | Network Intrusion | Weak firewall | Physical | Theft | Weak physical security
| Power Failure | Voltage fluctuations |  | DoS Attack | Insecure architecture |  | Unauthorized Entry | No access control
| Theft of Equipment | Lack of physical security |  | Eavesdropping | Unencrypted communication |  | Natural Disaster | Unsafe location
| Environmental Damage | Temperature / humidity issues |  | Data Interception | Exposed network |  | Fire | No fire detection
| Fire | Inadequate fire protection |  | Routing Issues | Poor network design |  | Flood | Poor infrastructure
| Water Damage | Poor facility protection |  | Unauthorized Access | Weak access control |  | Power Loss | No backup power
| Tampering | Weak access control |  | Overload | Lack of capacity planning | Governance | Policy Violation | Lack of policies
| Media Loss | Improper disposal | People | Human Error | Lack of training |  | Non-compliance | Weak controls
Software | Malware | Unpatched systems |  | Social Engineering | Low awareness |  | Data Manipulation | No audit trail
| Data Corruption | Poor validation |  | Insider Threat | Excess privileges |  | Poor Risk Management | No assessment process
| Unauthorized Access | Weak authentication |  | Fraud | Lack of monitoring |  | Audit Failure | Poor documentation
| Software Failure | Poor testing |  | Misuse of Systems | No policies |  | Access Mismanagement | No review process
| Tampering | Uncontrolled changes |  | Data Theft | Poor access control
| Pirated Software | Lack of compliance control |  | Negligence | Lack of accountability
| Key Logging | Insecure systems
| Application Error | Poor configuration

## Risk Heatmap
Likelihood
Impact | 1 | 2 | 3 | 4 | 5
5 | 15 | 30 | 45 | 60 | 75
4 | 12 | 24 | 36 | 48 | 60
3 | 9 | 18 | 27 | 36 | 45
2 | 6 | 12 | 18 | 24 | 30
1 | 3 | 6 | 9 | 12 | 15
1. Formula Used
Risk Score = Impact (I) × Likelihood (L) × Asset Value (A)
2. Risk Classification
Score | Level
51–75 | High
26–50 | Medium
0–25 | Low